Sprint Implementation Plan & Engineering Task Breakdown

RetailSync: Centralized Super Shop Warehouse Management System

Subtitle: 14-Week Agile Scrum Roadmap, Sprint Backlogs, Story Points, and Definition of Done

Course: SE-231 (Software System Analysis & Design / Capstone Project 2)

Academic Institution: Daffodil International University (DIU), Department of Software Engineering

Author: Raisul Islam Likhon (Section: SWE-44D)

Date: September 2026 | Version: 1.0.0-RELEASE

1. Scrum Framework Overview & Velocity Model

RetailSync follows an Agile Scrum Development Lifecycle structured across six 2-week sprints and a final 2-week hardening and defense preparation phase (14 weeks total):

Sprint Cadence: 2 weeks per sprint.

Sprint Planning: Day 1 of each sprint (2 hours).

Daily Standup: Asynchronous or 10-minute sync.

Sprint Review & Demo: Alternate Friday with academic supervisor / evaluators.

Definition of Done (DoD): Code committed to Git, unit tests passing (> 80% coverage), API endpoints documented in OpenAPI, database migrations reproducible via Docker, and UI responsive on mobile viewport (375x667).

+--------------------------------------------------------------------------------------------------------+ ¦ 14-WEEK CAPSTONE IMPLEMENTATION ROADMAP ¦ +--------------------------------------------------------------------------------------------------------+ ¦ Sprint 1 (W01-W02) ¦ Database Normalization, Core DDL Migrations, Auth & Next.js PWA Scaffolding ¦ ¦ Sprint 2 (W03-W04) ¦ Inbound PO Lifecycle, Handheld Barcode Dock Scanning, and Digital GRN Generation ¦ ¦ Sprint 3 (W05-W06) ¦ Directed Spatial Putaway Engine, 2D Floor Map & Real-Time FEFO Inventory Ledger ¦ ¦ Sprint 4 (W07-W08) ¦ Sub-2.0s POS Concurrency Deduction Engine, Row-Locking & Offline Caching Queue ¦ ¦ Sprint 5 (W09-W10) ¦ Replenishment DSS (EOQ, Greasley Safety Stock, ROP) & Outbound Wave Store Dispatch¦ ¦ Sprint 6 (W11-W12) ¦ Blind Cycle Counting, Shrinkage Anomaly Detection & Executive Floor Telemetry ¦ ¦ Sprint 7 (W13-W14) ¦ Concurrency Stress-Testing (Locust 50 req/s), Security Audit, Capstone Viva Demo ¦ +--------------------------------------------------------------------------------------------------------+

2. Sprint Backlogs & Granular Task Breakdowns

2.1 Sprint 1 (Weeks 1–2): Architecture, Relational Schema & Auth Core

Sprint Goal: Establish the reproducible Docker environment, initialize the 3NF PostgreSQL database, and deliver secure JWT authentication with role-based access control.

Target Velocity: 32 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-101 | Setup Docker Compose orchestrating PostgreSQL 16, Redis 7, FastAPI backend, and Next.js frontend. | DevOps & Infra | 5 | Single command docker compose up -d boots all containers with healthy status. |
| TSK-102 | Implement Alembic migration scripts for 15 core database tables and composite B-Tree indexes. | Data Modeling | 8 | alembic upgrade head runs cleanly; database schema passes 3NF verification audit. |
| TSK-103 | Load initial authentic seed data (5 suppliers, 7 SKUs, 6 bins, 6 batches, 3 stores). | Data Modeling | 3 | Seed script populates DB; verify foreign key constraints prevent orphaned records. |
| TSK-104 | Develop User entity, Argon2id password hashing, and JWT token issuance (/api/v1/auth/login). | Security & Auth | 5 | Pytest confirms valid token issued; invalid credentials return HTTP 401. |
| TSK-105 | Implement RBAC middleware enforcing permissions for Cashier, Operator, Clerk, Supervisor, Procurement. | Security & Auth | 5 | Test unauthorized route access returns HTTP 403 Forbidden. |
| TSK-106 | Scaffold Next.js 14 frontend design system with Tailwind CSS and responsive high-contrast layout. | Frontend PWA | 6 | Dashboard renders cleanly on mobile screen (375px) and desktop monitor (1920px). |

2.2 Sprint 2 (Weeks 3–4): Inbound PO & Handheld Barcode Dock Receiving

Sprint Goal: Deliver working dock receiving workflow allowing clerks to scan delivered carton barcodes against open POs and commit digital GRNs with damaged quarantine handling.

Target Velocity: 34 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-201 | Develop Supplier and Purchase Order CRUD API endpoints (/api/v1/suppliers, /api/v1/inbound/po). | Inbound Receiving | 5 | OpenAPI docs render PO status lifecycle transitions cleanly. |
| TSK-202 | Integrate Html5-QRCode / ZXing camera and Bluetooth scanner input in Next.js PWA. | Mobile Scanning | 8 | Scanner decodes EAN-13 barcodes in < 350 ms with audio beep feedback. |
| TSK-203 | Build PO line-item scan verification endpoint with remaining shelf-life check (≥ 75%). | Inbound Receiving | 5 | Batches with < 75% shelf life are flagged with visual rejection banner. |
| TSK-204 | Implement damaged carton logging with optional photo upload and quarantine status assignment. | Inbound Receiving | 5 | Quarantined units saved to product_batches with quarantine_status='QUARANTINED'. |
| TSK-205 | Build atomic GRN completion transaction generating digital GRN and supplier credit note advisory. | Inbound Receiving | 8 | Commits GRN; creates inventory_transactions records; updates PO to COMPLETED. |
| TSK-206 | Design printable internal warehouse carton/pallet barcode labels (EAN-128 format). | Inbound Receiving | 3 | Label layout prints cleanly on 4x6 inch thermal receipt/label printer. |

2.3 Sprint 3 (Weeks 5–6): Directed Putaway & Real-Time FEFO Inventory Ledger

Sprint Goal: Enable guided pallet putaway into warehouse bins and enforce automated First-Expired, First-Out (FEFO) batch priority allocation.

Target Velocity: 35 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-301 | Implement warehouse spatial bin layout API (locations) with zone and capacity constraints. | Spatial Putaway | 5 | Database rejects putaway suggestions into bins exceeding 500 kg or 300 units. |
| TSK-302 | Develop Directed Putaway recommendation algorithm factoring SKU velocity (ABC) and temperature. | Spatial Putaway | 8 | Class-A chilled milk correctly routed to Chilled Zone Aisle 1 near dispatch dock. |
| TSK-303 | Build mobile Directed Putaway PWA screen requiring destination bin scan confirmation. | Mobile Scanning | 5 | Operator cannot commit putaway without scanning the correct target bin barcode. |
| TSK-304 | Develop Real-Time FEFO Priority Queue sorting batches by ascending expiry_date. | FEFO Engine | 8 | API test verifies stock allocation always selects nearest valid expiry batch. |
| TSK-305 | Implement automated Expiry Watchlist background job (Safe, Watch, Warning, Critical ≤ 14 days). | FEFO Engine | 5 | Batches reaching expiration are automatically locked to quarantine_status='EXPIRED'. |
| TSK-306 | Build interactive 2D spatial bin occupancy floor map in Next.js using CSS Grid / Canvas. | Frontend Visual | 4 | Bins color-code dynamically: Green (< 70%), Amber (70-90%), Red (> 90%). |

2.4 Sprint 4 (Weeks 7–8): Sub-2.0s POS Sync API & Concurrency Row-Locking

Sprint Goal: Build and stress-test the real-time POS stock deduction API, guaranteeing sub-2.0s response times and zero deadlocks across multiple registers, backed by offline client caching.

Target Velocity: 36 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-401 | Implement /api/v1/pos/sync with pessimistic row-level locking (SELECT ... FOR UPDATE). | POS Concurrency | 8 | Automated benchmark demonstrates database lock duration < 25 milliseconds. |
| TSK-402 | Implement X-Idempotency-Key token validation in Redis with 48-hour TTL. | POS Concurrency | 5 | Replaying duplicate POST request returns cached confirmation without double-deduction. |
| TSK-403 | Develop POS register registry and telemetry heartbeat tracking online/offline status. | POS Concurrency | 5 | Dashboards highlight disconnected store cash registers in real time. |
| TSK-404 | Implement client-side Service Worker and encrypted IndexedDB offline sales queue. | Offline Resilience | 8 | Disconnecting network allows 20 scans locally; auto-syncs upon link reconnect. |
| TSK-405 | Develop bulk synchronization endpoint (/api/v1/pos/bulk-sync) for network recovery replay. | Offline Resilience | 5 | Bulk sync correctly processes 50 buffered offline transactions in order. |
| TSK-406 | Build Locust load-test script simulating 10 POS cashiers competing for the last unit of milk. | QA & Testing | 5 | 100% of race conditions resolve cleanly; zero negative inventory balances occur. |

2.5 Sprint 5 (Weeks 9–10): Replenishment DSS & Outbound Wave Dispatch

Sprint Goal: Implement mathematical inventory decision support models (EOQ, Greasley Safety Stock, ROP) and multi-branch outbound store wave picking.

Target Velocity: 33 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-501 | Implement Dynamic EOQ formula module using historical annual demand and holding costs. | Decision Support | 5 | Computed EOQ matches manual mathematical formula verification within 0.01%. |
| TSK-502 | Implement Greasley's Statistical Safety Stock formula factoring daily demand and vendor lead-time variance. | Decision Support | 8 | Output accounts for configured Z-scores (90%, 95%, 99%) and vendor \sigma_L. |
| TSK-503 | Build dynamic ROP alert engine triggering automated draft Purchase Orders for procurement review. | Decision Support | 5 | Falling below ROP generates pre-filled draft PO ready for one-click approval. |
| TSK-504 | Develop Branch Store Requisition Portal allowing store managers to submit weekly orders. | Store Requisition | 5 | Store order displays real-time central warehouse stock availability. |
| TSK-505 | Build Wave Picking consolidation algorithm aggregating multiple store requisitions into one wave. | Outbound Picking | 5 | Aggregates duplicate SKU requests into single bulk pick task. |
| TSK-506 | Implement shortest-path pick-list routing ordering picker travel by Aisle and Shelf sequence. | Outbound Picking | 5 | Picker walking distance reduced by > 40% compared to unsequenced list. |

2.6 Sprint 6 (Weeks 11–12): Cycle Counting, Anomaly Detection & BI Dashboards

Sprint Goal: Implement continuous blind cycle counting, unsupervised ML shrinkage anomaly detection, and executive KPI analytics.

Target Velocity: 30 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-601 | Implement Blind Cycle Counting sheets (system quantities hidden from floor counters). | Stocktaking & Audit | 5 | Mobile UI requires manual number input; reveals discrepancy only after submission. |
| TSK-602 | Build supervisor discrepancy approval workflow with mandatory reason codes and photo proofs. | Stocktaking & Audit | 5 | Adjustments > 1,000 BDT require supervisor authorization before ledger commit. |
| TSK-603 | Implement Scikit-learn IsolationForest model to detect anomalous shrinkage clusters. | Machine Learning | 8 | Model flags synthetic theft clusters across specific shift operators (F1 > 0.85). |
| TSK-604 | Build Executive KPI Dashboard (Total Inventory Value, GMROI, Turnover Ratio, Spoilage Rate). | Executive BI | 6 | Dashboard renders historical trends using Chart.js / Recharts with sub-1.5s load. |
| TSK-605 | Enforce database-level immutable audit ledger trigger on inventory_transactions. | Security & Audit | 6 | Direct SQL DELETE or UPDATE statements are blocked by database trigger exception. |

2.7 Sprint 7 (Weeks 13–14): Concurrency Stress-Testing, UAT & Viva Defense

Sprint Goal: Conduct comprehensive load testing (50 req/s), complete end-to-end user acceptance testing (UAT), and prepare the interactive defense presentation.

Target Velocity: 25 Story Points

| Task ID | Task Description | Epic | Est. Points | DoD Verification Step |
| --- | --- | --- | --- | --- |
| TSK-701 | Execute high-throughput Locust stress test (50 concurrent scanners, 10 POS registers). | Stress Testing | 8 | 99th percentile response time remains < 1.5 seconds with zero database errors. |
| TSK-702 | Conduct OWASP ZAP security vulnerability scan on all authentication and API endpoints. | Security Audit | 5 | Zero Critical or High vulnerabilities identified; SSL Labs A+ rating verified. |
| TSK-703 | Execute complete end-to-end UAT scenario covering receiving dock to retail POS checkout. | System Testing | 5 | All 6 personas execute workflows seamlessly on test hardware. |
| TSK-704 | Finalize Capstone Project Proposal Part 1 & Part 2 documentation and interactive slides. | Academic Defense | 7 | Deliverables compiled to PDF; interactive showcase dashboard deployed online. |